## Scrum Users and Events
Scrum Users and Event Matrix: Who Does what and when?
Scrum Users vs Events | Sprint Planning | Sprint Planning | Development Work | Daily Scrum | Sprint Review | Sprint Retrospective
Product Owner [1] |  | 1. Discuss the Sprint Objectives and create PBI out of them 2. What goal will be achiveved if the sprint objectives are completed 3. Clarify PBI to dev team and Make Trade-off/negotiate if the work is too small or too big
Scrum Master (1*)
Development Team (3 to 9) | Forcast the | 1. Forcast the functionality that will be developed: What can be done this sprint? 2. How the product functionlity will be built. 3. Develop a system design to convert PBI into Releasable Increments 4. Self organize and takeup the work (Tasks) 5. Dev team may invite technical/domain expert to the sprint planning for advice 5. Explain SM and PO, their development plan and Increment
All People is Scrum Team |  | 1. Collaborate on understanding the work o the sprint 2.
Other Key Stakeholder |  | 1. Domain or technical expert may help Dev Team give advice

## Interaction Matrix
Scrum Users Interaction Matrix
1. DURING SPRINT PLANNING
Scrum Users | Product Owner | Scrum Master | Development Team | Other Stakeholders
Product Owner
Scrum Master | Scrum Master says below to PO during Sprint Planning: 1. Sprint planning must take place for 8 Hours/4Week sprint and everyone must understand its purpose 2. No changes in the Sprint Goal should be done 2. What will be lost if the sprint gets cancelled 3. |  |  | 1. SM ensures the inputs given by stakeholders is helpful for the Scrum Team as whole
Development Team | 1. Clarification of Scope of work to the arbitratry level of details needed by dev team members
Other Stakeholders
2. DURING DAILY SCRUM
Scrum Users | Product Owner | Scrum Master | Development Team | Other Stakeholders
Product Owner
Scrum Master | 1. No changes in the Sprint Goal should be done
Development Team | 1. Negoatiate the scope of work item based
Other Stakeholders
3. DURING DEVELOPMENT WORK
Scrum Users | Product Owner | Scrum Master | Development Team | Other Stakeholders
Product Owner
Scrum Master
Development Team
Other Stakeholders
4. DURING SPRINT REVIEW
Scrum Users | Product Owner | Scrum Master | Development Team | Other Stakeholders
Product Owner
Scrum Master
Development Team
Other Stakeholders
5. DURING SPRINT RETROSPECTIVE
Scrum Users | Product Owner | Scrum Master | Development Team | Other Stakeholders
Product Owner
Scrum Master
Development Team
Other Stakeholders